## Sprint Backlog 2
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
List User Story steps that were not completed at Sprint End

## Sprint Backlog 1
| User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | USBookCSMT:001 | 1 | Class Design | Shreyanka | 13/7/2020 | 4 hr | 2 hrs | Completed | 1 hr
|  | 2 | Interface Design | Shreyanka | 13/7/2020 | 4 hr | 2 hrs | Completed | 1 hr
2 | USBookCSMT:002 | 1 | Test plan | Shreyanka | 14/7/2020 | 2 hr | 1 hr | Completed | 1 hr
3 | USBookCSMT:003 | 1 | Creating a Spring boot starter Project | Shreyanka | 14/7/2020 | 2 hr | 1 hr
4 | USBookCSMT:004 | 1 | Entity Class Design