## Sprint Backlog 2
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
| USBookCSMT:001 | 1 | Wireframes and story boarding for each | Shreyanka | 2020-07-22 | 2 hr | 1 hr | Completed | 1 hr
|  | 2 | Routing Url List | Shreyanka | 2020-07-22 | 2 hr | 1 hr | Completed | 1 hr
|  | 3 | Data classes details | Shreyanka | 2020-07-23 | 2 hr | 1 hr | Completed | 1 hr
|  | 4 | Angular service | Shreyanka | 2020-07-23 | 2 hr | 1 hr | Completed | 1 hr
|  | 5 | Components details | Shreyanka | 2020-07-23 | 2 hr | 1 hr | Completed | 1 hr
| USBookCSMT:002 | 1 | View Component of order | Shreyanka | 2020-07-24 | 4 hr | 2 hr | Completed | 2 hr
| USBookCSMT:003 | 1 | Add Component of order | Shreyanka | 2020-07-25 | 4 hr | 2 hr | Completed | 2 hr
| USBookCSMT:004 | 1 | service class of order | Shreyanka | 2020-07-26 | 4 hr | 2 hr | Completed | 2 hr
List User Story steps that were not completed at Sprint End
Note on A3: ====== ID#AAAAGgjMX2U (2020-05-13 08:35:50) This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B3: ====== ID#AAAAGgjMX1c (2020-05-13 08:35:50) This column is used to document the Use Case Identifier.
Note on D3: ====== ID#AAAAGgjMX14 (2020-05-13 08:35:50) Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E3: ====== ID#AAAAGgjMX20 (2020-05-13 08:35:50) List the Scrum team members assigned to this task.
Note on F3: ====== ID#AAAAGgjMX0g (2020-05-13 08:35:50) Column is used to document the date the task was assigned
Note on G3: ====== ID#AAAAGgjMX28 (2020-05-13 08:35:50) Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H3: ====== ID#AAAAGgjMX2w (2020-05-13 08:35:50) Adjusted estimate after the Sprint has begun
Note on I3: ====== ID#AAAAGgjMX1g Task status (2020-05-13 08:35:50) Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J3: ====== ID#AAAAGgjMX0k (2020-05-13 08:35:50) Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K3: ====== ID#AAAAGgjMX2o (2020-05-13 08:35:50) Use this column to provide supporting information such as changes to the original requirement.
Note on M3: ====== ID#AAAAGgjMX24 (2020-05-13 08:35:50) This column is used to link the requirements to any resulting modules (software).
Note on N3: ====== ID#AAAAGgjMX0M (2020-05-13 08:35:50) This column is used to link the requirements/use cases to the test scenarios.
Note on O3: ====== ID#AAAAGgjMX04 (2020-05-13 08:35:50) This column is used to link the requirements/use cases to the test scenarios.
Note on P3: ====== ID#AAAAGgjMX00 (2020-05-13 08:35:50) This column is used to link the requirements/use cases to the test scenarios.

## Sprint Backlog 1
| User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | USBookCSMT:001 | 1 | Class Design | Shreyanka | 2020-07-13 | 4 hr | 2 hrs | Completed | 1 hr
|  | 2 | Interface Design | Shreyanka | 2020-07-13 | 4 hr | 2 hrs | Completed | 1 hr
2 | USBookCSMT:002 | 1 | Test plan | Shreyanka | 2020-07-14 | 2 hr | 1 hr | Completed | 1 hr
2020-07-14
3 | USBookCSMT:003 | 1 | Creating a Spring boot starter Project | Shreyanka | 2020-07-14 | 2 hr | 1 hr | Completed | 1 hr
4 | USBookCSMT:004 | 1 | Entity Class Design of Customer and table created | Shreyanka | 2020-07-15 | 2 hr | 1 hr | Completed | 1 hr
|  | 2 | Entity Class Design of Book and table created | Shreyanka | 2020-07-15 | 2 hr | 1 hr | Completed | 1 hr
|  | 3 | Entity Class Design of OrderDetail and table created | Shreyanka | 2020-07-15 | 2 hr | 1 hr | Completed | 1 hr
5 | USBookCSMT:005 | 1 | DAO implementation of customer | Shreyanka | 2020-07-15 | 2 hr | 1 hr | Completed | 1 hr
|  | 2 | DAO implementation of Book | Shreyanka | 2020-07-15 | 2 hr | 1 hr | Completed | 1 hr
|  | 3 | DAO implementation of OrderDetails | Shreyanka | 2020-07-15 | 2 hr | 1 hr | Completed | 1 hr
6 | USBookCSMT:006 | 1 | Service implementation of OrderDetail | Shreyanka | 2020-07-16 | 4 hr | 2 hr | Completed | 1 hr
7 | USBookCSMT:007 | 1 | Controller implementation of OrderDetail | Shreyanka | 2020-07-16 | 2 hr | 1 hr | Completed | 1 hr
Note on A3: ====== ID#AAAAGgjMX2Y (2020-05-13 08:35:50) This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B3: ====== ID#AAAAGgjMX2Q (2020-05-13 08:35:50) This column is used to document the Use Case Identifier.
Note on D3: ====== ID#AAAAGgjMX3A (2020-05-13 08:35:50) Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E3: ====== ID#AAAAGgjMX2A (2020-05-13 08:35:50) List the Scrum team members assigned to this task.
Note on F3: ====== ID#AAAAGgjMX1E (2020-05-13 08:35:50) Column is used to document the date the task was assigned
Note on G3: ====== ID#AAAAGgjMX1Y (2020-05-13 08:35:50) Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H3: ====== ID#AAAAGgjMX1o (2020-05-13 08:35:50) Adjusted estimate after the Sprint has begun
Note on I3: ====== ID#AAAAGgjMX3E Task status (2020-05-13 08:35:50) Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J3: ====== ID#AAAAGgjMX2E (2020-05-13 08:35:50) Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K3: ====== ID#AAAAGgjMX2g (2020-05-13 08:35:50) Use this column to provide supporting information such as changes to the original requirement.
Note on M3: ====== ID#AAAAGgjMX1k (2020-05-13 08:35:50) This column is used to link the requirements to any resulting modules (software).
Note on N3: ====== ID#AAAAGgjMX1M (2020-05-13 08:35:50) This column is used to link the requirements/use cases to the test scenarios.
Note on O3: ====== ID#AAAAGgjMX2k (2020-05-13 08:35:50) This column is used to link the requirements/use cases to the test scenarios.
Note on P3: ====== ID#AAAAGgjMX0Y (2020-05-13 08:35:50) This column is used to link the requirements/use cases to the test scenarios.